## Risk Log
Project Name: |  | HCIP
Project Manager: |  | Randall Alberts, PMP
Revision Date: |  | 2005-05-05
Number | Risk |  | Level | Currently Assigned | Risk Strategy | Risk Plan
Example | Supply from vendor is on backorder and will not be shipped for two weeks. This part is needed for the xyz system to function properly. |  |  | John Doe | - Mitigate | Supply Chain will review the situtation with vendor and determine if there are additional sources available to purchase item. If no aditional resources are availbe, then project team will adjust project plan. | +- Accept
1 | [6 empty] | - Avoid
2 | [6 empty] | - Mitigate
3 | [6 empty] | - Transfer
4 | [6 empty] | + Exploit
5 | [6 empty] | + Share
6 | [6 empty] | + Enhance
7
8
Risk Analysis

## Avoided Risks
Project Name: |  | HCIP
Project Manager: |  | Randall Alberts, PMP
Revision Date: |  | 2005-05-05
Number | Risk |  | Level | Currently Assigned | Recommended/Final Mitigation
2 | Dollars for Troy and Mark's Remedy training. One of the likely impacts is the inability to report metrics. |  |  |  | Training Budet Has been approved for Phase I
7 | June's position does not get reclassified to Data Manager. |  |  |  | June Moss' position was classified as a data manager to perform the functions needed for this project
8 | PM not hired or significantly delayed. |  |  | Mary Jane Casto | PM hired as of May 2nd. No longer and issue.
Risk Analysis