## Slide 1
To Scrum or Kanban: Is that the Question?
Candace Jones Senior Applications Manager University of California, Office of the President

## Slide 2: Agenda
Introduction
Round 1: Basic Agile Principles
Round 2: Scrum
Round 3: Scrumban
Sample Project
How can I get started?

## Slide 3
Introduction

## Slide 4
University of California
  Ten campuses, five medical centers, and three
  national laboratories
  We serve 233,000 students and 190,000 employees
  We have a budget of approximately 24 billion dollars
  Office of the President – 1500 staff across 60
  departments
Web and Application Services Undergraduate Admissions Systems
  Over 80 custom PHP applications
  Central Undergraduate Admissions Application
  Drupal and Cascade Server
  SharePoint

## Slide 5: Discussion
PollEv.com/candacejones126

## Slide 6
Basic Agile Principles

## Slide 7: Agile Manifesto
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
Individuals and interactions over processes and tools Working software over comprehensive documentation Customer collaboration over contract negotiation Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.

## Slide 8: Scrum versus Kanban
Scrum
  Product owner, ScrumMaster, Team
  Sprint planning, timeboxed sprints, sprint demo,
  retrospectives
  Set explicit policies
Kanban
  No defined roles, less prescriptive
  Visualize the workflow
  Set work in progress limits

## Slide 9
Scrum

## Slide 10: President’s Postdoctoral Fellowship Program
Entire team attended training – Passed Certified
ScrumMaster test
Project already behind schedule before starting new
methodology
Team formed - sprint planning, estimates, daily stand-ups
Sprint demo one – delayed, conducted retrospective
  $40,000 = 579 Hours
  Overage = 413 hours or $35,000
Committed to finishing PPFP with Scrum

## Slide 11: Down but not out!

## Slide 12: What went wrong?
Candace Jones
Estimates inaccurate
Stand-ups too long (debating roadblocks)
Retrospectives quiet
Took on too large a project for first Scrum experience.

## Slide 13
Round 3: Coaching / Scrumban

## Slide 14: Retrospective / Coaching
Brought in Agile Coach to participate in Retrospective
  Appreciated the planning in Scrum
  Maintenance work never taken into account
  Need one place to manage both
  Need explicit policies to apply to work
  Resource assignments needed to be adjusted
  Okay to switch methodologies

## Slide 15: Sample Project
RGPO Donation Form
  Users stories
  Project list
  Kanban board
  Quick demo

## Slide 17: How do I get started?
Start small……take something that would take you less than 40 hours to complete and schedule it across a two week sprint.
  This extra time will not place undue pressure for first project
  It also will allow the team to feel a bit of success initially.
Chose a project that either you have a flexible customer – or is internally facing, to the unit.
Get training / coaching.

## Slide 18: Discussion
PollEv.com/candacejones126

## Slide 19: Help Us Improve and Grow
Thank you for participating
in today’s session.
We’re very interested in your feedback. Please take
a minute to fill out the session evaluation found within
the conference mobile app, or the online agenda.