## Business Case Guide
Business Case Guide
ABOUT BUSINESS CASES
Business cases are the means to request projects and services that involve the use of shared resources. The information collected in a business case informs decision makers of the associated strategic alignment, costs, benefits, and risks so they can select and prioritize requests. Email pmo@montana.edu to initiate a request. The Program Management Office assists requestors in completing the business case. All requests are captured at a high level on the Summary page. Small requests may be expedited directly into Implementation without further business case development. Complex requests may need further development to discover costs and requirements, using detailed worksheets. Unhide worksheets if needed. See the overview and detailed explanation of the process provided below, as well as a brief glossary of related terms and explanation of project stages.
PURPOSE
The business case template serves multiple purposes: w Capture the initial concept of a request to get it into the queue and keep track of it. The Concept page alone is used. w Record an historical project accomplishment that did not go through the standard process. The Summary page alone is used. w Analyze Cost/Benefit/Risk associated with a proposed project. The entire business case tempate is used, with supporting analysis as needed. w Inform decision makers of costs, benefits, risks, and strategic alignment to select and prioritize project requests. w Authorize shared resources to work on business case development (Discovery) or project development (Implementation).
STAGES LEGEND
Intake | A requestor providers information to the PMO to initiate the business case and enter the request into the queue as a Concept.
Concept | The request has been captured in an initial high-level business case. Concept Clearance approves and prioritizes the Concept for the Discovery stage.
Discovery | The Program Management Office works with the requestor and Subject Matter Experts to analyze cost, benefit, risk, and strategic alignment in preparation for prioritization by the governing body.
Implementation | The project has been prioritized and resourced. Detailed planning and scheduling is in progress and may result in adjustments to priorities. Implementation status is monitored and reported by the PMO.
Inactive | Progress on the project has been halted, at any stage of its lifecycle. The project is monitored for a future opportunity.
PROCESS OVERVIEW
PROJECT INTAKE PROCESS EXPLANATION
GLOSSARY OF TERMS
Executive Sponsor | The individual at the VP, Chancellor, or Vice-Chancellor level on any campus who lobbies for a project, represents it to the governing body, and is prepared to provide financial backing. Projects do not proceed beyond Concept stage without an executive sponsor.
PMO | A Program Management Office provides any combination of governance, planning, portfolio, program, procurement, and project management services and support to the organization. Also commonly referred to as a Project Management Office.
Portfolio | A collection of programs and projects across the enterprise that are managed as a strategic investment. Like a financial portfolio, projects and programs are continually assessed and prioritized to be sustained, enhanced, expedited, suspended or removed from the portfolio.
Program | A collection of interrelated projects with a common goal that benefit from collective management. Many IT implementations are institutional programs that affect a wide range of constituents.
Project | A significant package of work that has a beginning, end, and unique output. A project can be a solution to implement or research to investigate a solution, or it could be many other things.
Shared Resources | Any resources of the university--human, technological or financial--that are shared by more than one administrative or academic unit.
Stage | Projects and programs move through a series of stages beginning with Concept where high-level information is gathered to develop a business case. Stages are defined in the legend provided.
Stage-Gate | Projects and programs are evaluated and approved to move from one stage to the next. The decision point between stages is referred to as a stage-gate. Projects and programs can be theoretically re-prioritized, slowed, expedited, or rendered inactive at any stage-gate.
Intake: Request is received by the PMO; initial business case is captured with requestor to create a record of the request.
Concept: Proposed solution is entered into the portfolio with high-level cost, benefit, risk, alignment information; waits for clearance into Discovery.
Concept Clearance: Council reviews Concepts and
a) prioritizes into Discovery, or
b) expedites, or
c) holds as Concept; the PMO monitors for future opportunity.
Discovery: Proposed solution is further researched and elaborated with detailed cost information.
Solution Prioritization: Council reviews detailed solutions and
a) prioritizes for implementation, or
b) requests further evaluation, or
c) holds for future prioritization; the PMO monitors for future opportunity.
Investment: Acquisition, Planning, and Implementation stages require institutional investment in the solution.
Acquisition: If products or services must be acquired, the PMO supports procurement and contract development.
Planning: Implementation projects are planned by the project manager and technical leads with PMO support.
Implementation: Planned solutions are implemented as projects or programs.
Expedite: The Council may request to expedite a solution for regulatory compliance, executive mandate, information security, or exigency.
Evaluate Further: Solutions lacking sufficient information to approve or prioritize return to Discovery for additional analysis.
On Hold: Solutions that are not selected for discovery or prioritization remain in the portfolio for future consideration.

## Summary
[Enter Project Name] |  |  | BUSINESS CASE |  |  | STAGE |  |  | [Select Stage]
OVERVIEW
Requestor | [5 empty] | Request Date
Title | [5 empty] | Email
Department | [5 empty] | Phone
Executive Sponsor | [5 empty] | Timeframe
Project Sponsor | [5 empty] | Funding
Project Manager | [5 empty] | Source
Program
Opportunity Statement |  | [Describe the problem you are trying to solve or the opportunity you want to leverage]
Proposed Solution |  | [Describe what you are picturing as a solution]
Alternative Solutions |  | [Describe the possible alternatives that you have considered, any that you have discarded and why.]
General Time & Effort |  | [Compared to other projects, is this small, medium, large, XL? How many staff hours do you think it will take to do this, across the university?]
Success Criteria |  | [When this project is completed, what does success look like?]
Risks |  | [What challenges do you foresee for this project?]
STRATEGIC ALIGNMENT
Campuses
Constituents
Mission Support
Drivers
Business Criticality |  | [Select from list] |  | [Explain]
BZ Strategic Objectives |  | [List strategic plan objectives or other institutional objectives this project supports]
BL Strategic Objectives
GF Strategic Objectives
HV Strategic Objectives
Positive Impact |  | [Describe how the communities checked above will benefit from this solution.]
COST AND REQUIREMENTS
Request Type
Upfront Requirements
Upfront Real Cost |  |  |  | Upfront T&E Cost
Ongoing Requirements
Ongoing Annual Cost |  |  |  | Ongoing Annual T&E Cost
COMMENTS AND RECOMMENDATIONS
Investment | 0 | Strategic Alignment |  | 0% | Value |  | 0% | Probability of Success |  | 0%
Development
Enhancement
Upgrade
System Integration
Process Redesign
Regulatory
Information Security
Maintenance
Discretionary
Bozeman
Billings
Havre
Great Falls
Students
Faculty
Staff
Taxpayers
Software
Hardware
Services
Time & Effort
Software
Hardware
Services
Time & Effort
Operational Efficiency
Customer Service
Infrastructure
Patrons
Mandatory
Decision Support
Note on A28: Hall, Ellen: Campus strategic objective info is located in a folder called campus_strategic_plans located in th PMO share: PMO/Templates/Business Case/campus_strategic_plans (not a link) Please contact PMO if you don't have access to the share.

## Charter (hidden)
[Enter Project Name] | PROJECT CHARTER |  | STAGE |  | [Select Stage]
Charge Summary
[What exactly are we doing (at a high level)?]
Objectives
[What must be achieved to consider this project successful?]
High Level Deliverables
[What are the high level deliverables (bullets) of this project or program?]
Key Milestones
[What are the key milestones (bullets) of this project or program?]
Authorization
Executive Sponsor |  | Signature |  | Date
Project Sponsor |  | Signature |  | Date
Enterprise CIO |  | Signature |  | Date
Adam Edelman
Associate CIO, IT Governance |  | Signature |  | Date
Anne Milkovich

## Scope (hidden)
[Enter Project Name] | BUSINESS CASE | STAGE | [Select Stage]
PROJECT SCOPE
Check or describe the high-level tasks and activities included in the scope of this project
Describe tasks or activities explicitly INCLUDED in the scope of this project
Describe tasks or activities explicitly EXCLUDED from the scope of this project
List the known assumptions contributing to the scope, cost, or other components of this project
Who are the stakeholders in this project? (List stakeholders and their interests)
What alternatives exist for this project? (Describe alternatives that could achieve similar results)
Gather Requirements
Identify end users
Develop and publish RFP or other procurement
Identify training needs and conduct training
Identify reporting needs and create reports
Identify and develop integration points
Work with 3rd-party non-partner vendors
Work with 3rd-party partner vendor
Create and execute communication plan
Create Service Level Agreement
Develop test bed
Perform developer testing
Perform user acceptance testing
Move application into production
Develop user/developer documentation
Handle inquiries and user support
Spec, purchase, install hardware
Customize 3rd party sw/hw
Migrate/convert data
Maint/Support with vendor
Security reviews

## Benefit (hidden)
[Enter Project Name] | BUSINESS CASE |  | STAGE | [Select Stage]
BENEFIT
Benefits Summary Check all that apply
Community Experience | Fiscal |  | Mission
Other: | Other: |  | Other:
Operational Efficiency |  | Sustainment
Other: |  | Other:
What are the expected tangible or intangible benefits of the outcome? Describe
What is the background behind this project? Describe any relevant background information
Who are the intended end users? Check all that apply
Expected number of end users directly benefiting? Select one
What are the expected cost or effort savings? Attach supporting documentation if necessary
Description |  |  |  |  | Estimated Savings
What are the expected annual revenue gains? Attach supporting documentation if necessary
Description |  |  |  |  | Estimated Gain
How do the benefits of the alternative solutions compare to this solution? Describe or attach alternatives analysis
Improved external customer service
Improved internal customer service
Improved student experience
Reduced costs
Increased revenue
Improved research support
Improved outreach support
Improved instruction support
Improved business process
Improved decision support
Leveraged opportunity
Increased productivity
Improved resource utilitization
Information security
Improved infrastructure
Regulatory compliance
Risk mitigation
Students
Advisors
Faculty
Colleges/Academic staff
Administrative/Central staff
Functional Area Unit:
Fewer than 20 users
Between 20 and 100 users
Between 100 and 500 users
Between 500 and 2500 users
Between 2500 and 5000 users
Greater than 5000 users

## Cost (hidden)
[Enter Project Name] |  | BUSINESS CASE | STAGE |  | [Select Stage]
COST
Upfront Product Acquisition Costs Check all that apply, describe, enter cost estimates
Type of Cost | Description |  |  |  |  | Estimated Cost
Product Procurement Information
Have vendor options been identified?
What procurement will be required?
What is the procurement status?
Upfront Consulting Service Acquisition Costs
Description | [5 empty] | Estimated Cost
Service Procurement Information
Have vendor options been identified?
What procurement will be required?
What is the procurement status?
Existing Technology Infrastructure to be used Check all that apply, describe, enter cost estimates
Type of Cost | Description |  |  |  |  | Estimated Cost
Upfront Development / Integration Time & Effort Costs Use average burdened rates and/or hourly equation provided
Type | Name |  | Est. Hours | Avg Rate |  | Estimated Cost
|  |  |  | 60 |  | 0
|  |  |  | 55 |  | 0
|  |  |  | 55 |  | 0
|  |  |  | 70 |  | 0
|  |  |  | 55 |  | 0
|  |  |  | 55 |  | 0
|  |  |  | 60 |  | 0
|  |  |  | 55 |  | 0
|  |  |  | 50 |  | 0
|  |  |  | 50 |  | 0
|  |  |  | 50 |  | 0
|  |  |  | 60 |  | 0
|  |  |  | 55 |  | 0
|  |  |  | 30 |  | 0
|  |  |  | 30 |  | 0
|  |  |  | 70 |  | 0
Type | Name |  | Est. Hours | HrlyRt | *k | Estimated Cost
[5 empty] | 1.75 | 0
[5 empty] | 1.75 | 0
[5 empty] | 1.75 | 0
[5 empty] | 1.75 | 0
Upfront Development / Integration Cash Outlay Costs Check all that apply, describe, enter cost estimates
Type of Cost | Description |  |  |  |  | Estimated Cost
Upfront User Support Costs Check all that apply, describe, enter cost estimates
Type of Cost | Description |  |  |  |  | Estimated Cost
Ongoing Annual Costs Check all that apply, describe, enter cost estimates
Type of Cost | Description |  |  |  |  | Estmtd Annual Cost
(estimate 20% of upfront development)
How do the costs of the alternative solutions compare to this solution? Describe or attach alternatives analysis
Hardware purchase
Software purchase
Other purchase
Hardware
Software
Bandwidth
Licensing
Vendor support
Other T&E costs
Training: Instructor
Training: Learners
Materials
User Support
Other cash costs
Functional area labor
Internal IT labor
User support labor
Other T&E costs
Programmer
Programmer
Sr. Programmer
Security Analyst
Module Team Lead
Project Manager
Business Analyst
Sr. Systems Admin
Systems Admin
Communicatns Support
Web Developer
IT Director
Sr. Functnl Area Staff
Functional Area Staff
Other labor cost
Other labor cost
Sr. Database Admin
Database Admin
Sr. Network Analyst
Network Analyst
3rd-party consulting
Other Costs
Other Costs
3rd-party consulting
Other cash costs

## Risk (hidden)
[Enter Project Name] | BUSINESS CASE |  | STAGE | [Select Stage]
RISK
Critical Success Factors Explain the things that MUST happen for this project to succeed
Describe the alignment of underlying technology to current and emerging industry best practices
Describe the likelihood of risks and their impact if this project is NOT implemented
Describe the likelihood of risks and their impact if this project IS implemented
Describe the life expectancy of the product as a long-term or short-term solution Describe or attach alternatives analysis
Describe the likelihood of risks and impacts of alternative solutions Describe or attach alternatives analysis
Describe the probable level of internal support needed for the life of the product Describe or attach alternatives analysis
Describe the vendor qualifications, history, and track record of support Describe or attach alternatives analysis
Expected number of end users to be trained? Select one
Describe the knowledge base and level of training needed
Describe the communications plan
Describe the security review and analysis
Expected number of users otherwise impacted? Select one
Describe the impact on the users e.g. inquiry handling, new procedures, internal support
What prior project is this project most similar to? Describe how they are similar and/or different
Dependencies Select one or more |  | Dependency Details Explain
Fewer than 20 users
Between 20 and 100 users
Between 100 and 500 users
Between 500 and 2500 users
Between 2500 and 5000 users
Greater than 5000 users
Fewer than 20 users
Between 20 and 100 users
Between 100 and 500 users
Between 500 and 2500 users
Between 2500 and 5000 users
Greater than 5000 users
Other applications are IMPACTED by this project
Other applications are REQUIRED for this project
No dependencies exist for this project

## Rubric (hidden)
[Enter Project Name]
REF | CATEGORY | FACTOR | OBJECTIVE | VALUE
ALIGNMENT |  |  |  | 0%
A.1 | Mission | Discovery | Outcome directly addresses mission-aligned discovery and research objectives. | 0
A.2 | Mission | Engagement | Outcome directly addresses mission-aligned engagement and outreach objectives. | 0
A.3 | Mission | Learning | Outcome directly addresses mission-aligned learning and teaching objectives. | 0
A.4 | Mission | Campus Strategies | Outcome directly addresses the strategic objectives of all MSU campuses. | 0
A.5 | Mission | Student Experience | Outcome results in significantly improved student experience. | 0
A.6 | Mission Support | Decision Support | Outcome results in significantly improved decision making support. | 0
A.7 | Mission Support | Operational Efficiency | Outcome results in optimized operational efficiency. | 0
A.8 | Mission Support | Customer Service | Outcome results in significantly improved internal customer service. | 0
A.9 | Constituents | Constituents | Outcome addresses the needs of the widest range of constituents. | 0
A.10 | Stewardship | Integration | Outcome integrates the operations of all MSU campuses. | 0
A.11 | Stewardship | Infrastructure | Outcome directly sustains or needfully enhances mission-critical infrastructure. | 0
A.12 | Stewardship | Risk Mitigation | Outcome reduces, mitigates, or avoids risk. | 0
VALUE (Cost Effectiveness) |  |  |  | 0%
V.1 | Cost | Ongoing | Ongoing cost is minimal or none. | 0
V.2 | Cost | Upfront | Upfront cost is minimal or none. | 0
V.3 | Fiscal | Cost Savings | Outcome reduces cash outflow. | 0
V.4 | Fiscal | Time Savings | Outcome reduces time on process. | 0
V.5 | Fiscal | Revenue Increase | Outcome directly increases revenue inflow. | 0
V.6 | Fiscal | Optimization | Outcome directly optimizes use of internal and/or external resources. | 0
V.7 | Utilization | IT Resources | Utilization of existing IT hardware/software/network T&E is minimal or none. | 0
V.8 | Utilization | IT Labor | Utilization of existing IT T&E in hidden costs is minimal or none. | 0
V.9 | Utilization | Functional Labor | Utilization of existing functional area T&E in hidden costs is minimal or none. | 0
RISK (Probability of Success) |  |  |  | 0%
R.1 | Institutional | Critical Success Factors | CSFs are achievable with a high probability of occurring easily. | 0
R.2 | Institutional | Funding Availability | Upfront and ongoing funding is sufficient for the life of the project. | 0
R.3 | Institutional | Organizational Readiness | The institution is ready and willing to adopt this solution over alternatives. | 0
R.4 | Planning | Training | Training needed is minimal and has been adequately planned for. | 0
R.5 | Planning | Measurement | Outcome performance is measurable and will be reported. | 0
R.6 | Planning | Stakeholders | Stakeholders are identified; expectations are reasonable and manageable. | 0
R.7 | Planning | Security Controls | Information security controls have been thoroughly vetted and accounted for. | 0
R.8 | Scope | Complexity | Complexity is minimal; scope is defined and manageable | 0
R.9 | Scope | Dependencies | Project dependencies and impacts have been reliably identified. | 0
R.10 | Sustainability | Life Expectancy | The product purchased or implemented has a high probability of long-term viability. | 0
R.11 | Sustainability | Vendor Qualifications | The vendor is the highest qualified with a strong track record of quality support. | 0
INVESTMENT
Considering all the above factors, do you believe this project will Run, Grow, or Transform institutional performance?

## Stakeholder Register (hidden)
[Enter Project Name] | BUSINESS CASE | [5 empty] | STAGE | [Select Stage]
STAKEHOLDER REGISTER
Name |  | Title | Department | Role on Project | Email | Phone | Campus | Comments
Note on M3: Hall, Ellen: Click to see role definitions on Look up sheet.

## LOOKUP (hidden)
0 | [Select Stage] | [Select] | [Select]
1 | Concept | BL | Executive | The executive role is any person in the organization who has financial responsibility and/or accountability for the project.
2 | Discovery | BZ | Functional | The functional role describes any person who uses the product or process enough to know whether or not it works. They do not fix the product.
3 | Acquisition | GF | Technical | The technical role describes any person who works with the product to troubleshoot, install, configure, and integrate current and new software (Do we need to mention the vendor?).
4 | Planning | HV | Project | The project role describes any person with administrative duties for the project but does not have an executive, functional or technical role.
5 | Implementation | 4-campus
NA
Pending
| [Select from list] | [Select]
Unit Valuable
| Unit Essential | Run
| Unit Critical | Grow
| Campus Valuable | Transform
Campus Essential
Campus Critical
Enterprise Valuable
Enterprise Essential
Enterprise Critical