## Slide 1: A Story of Openness: The Transition From Blackboard Vista to Moodle
J. Garvey Pyke, Ed.D.
Nicole Harris
Center for Teaching and Learning,
University of North Carolina at Charlotte

## Slide 2: Timeline
Spr.
2007
Transition from WebCT to Blackboard Vista
Spr.
2008
Campus discussion on alternative LMS. Evaluation committee formed.
Fall
2008
Limited pilot.
12 faculty, 23 courses,
850 students
Spr.
2009
Fall
2009
Expanded pilot.
40 faculty,
90 courses,
3000 students
Opened to campus.
Spr.
2011
Migration 97% complete.
Sum.
2009
Moodle adopted.
18 Months: Evaluation
24 Months:
Migration

## Slide 3: Blackboard Vista
Campus in Crisis
  Anecdotal unhappiness
  System outages
  Closed process for picking WebCT Vista
  Blackboard purchased WebCT
  Cost increased
  Customer service decreased
  New director, new CIO

## Slide 4: LMS Evaluation
Philosophy:
Unlike usual IT processes, it was
  Collaborative
  Open
  Inclusive
  Faculty Led
  Data Driven

## Slide 5: Openness Strategies
LMS Evaluation Committee
  Faculty
  Instructional staff
  IT staff (central and distributed)
  Students
  Chaired by two respected faculty leaders
  Appointed by the Provost
Public LMS Evaluation Website
  Minutes
  Data
  Rubrics
  Discussion
  Documentation

## Slide 7: Openness Strategies, Cont.
Communications Plan
  LMS website
  CTL website
  University listservs
  Campus News
  Faculty Council briefings
  Deans Council meetings
  College, departmental meetings
  Distributed responsibility

## Slide 8: Data Collection Strategies
Faculty Survey
  Satisfaction with BB [58%]
  Willingness to Change LMS [65%]
  Tools & Practices*
Student Survey
  Satisfaction with BB [44%]
  Cited access issues, value of BB
Evaluation Rubric*
  Categories
  Weighted
  Instructional and technical

## Slide 9: Data Collection, Cont.
Total Cost of Ownership Comparisons
  BB external hosting, licensing, plus internal staff
  Other LMS scenarios [internal/external hosting, et al.] plus internal staff
Demo/Test LMS
  Moodle
  Sakai
  Blackboard
  Angel
  D2L
Timeline reminder:
6 months to get to a pilot recommendation; next 12 months spent on pilot

## Slide 10: Pilot Process
Two Stage Pilot
  Fall: 12 Faculty, 23 courses, 850 students
  Spring: 40 faculty, 93 courses, 3000 students
Data Collection – Rubric Based
  Surveys: faculty, students
    Ease of use, training needs, reliability, usefulness
    80+% preferred Moodle in both groups
  Focus groups: faculty, students
Communications Plan Continued
Final Report & Recommendation

## Slide 11: Two-Year Migration
Dual LMS Support
Training Strategies
  Online and F2F
Moodle Success Was Immediate
  1st semester adoption exceeded BB: 650 faculty, 800 courses, 18000 students
  Fall 2010: 1000 faculty, 1900 courses, 22000 students
Moodle Enhancement Process
  Continued openness
  Enhancement request forum
  Faculty Moodle Enhancement Committee
  Communications/marketing plan

## Slide 12: Final Considerations
Culture & Context
  Large core of active faculty who take shared governance seriously
  Central IT involvement
  Desire for openness
Take Your Time
Collect Data
Continue the Collaborative Process Post-Implementation
“Greater Openness Leads to Greater Adoption”

## Slide 13: More Info
http://lmseval.uncc.edu
http://teaching.uncc.edu