## Slide 1: Technology Project Selection and Governance at Loyola University Maryland
Richard G. Sigler, Director PMO
Loyola University Maryland

## Slide 2: Bringing process: building something great
Loyola recognized the need for process
  no more arbitrary “yes & no”
  selection process must be repeatable & consistent
  must represent the strategic and evolving needs
  the University must be involved and “buy in”
  projects must be tracked and managed in a portfolio
  increase project success

## Slide 3
Loyola decided we needed a
PMO

## Slide 4: How do we do that?

## Slide 8: PMO
Invest Well
Increase Success
Lower Risk
Increase Maturity
Show Progress

## Slide 9
Project Portfolio
PM Process
Information System (PPM / PM Info Sys)
Support Strategy

## Slide 10: Project Portfolio
Formation
Tracking
Reporting

## Slide 11: Portfolio Formation – Step 1 Proposal
Actor: Organization Member
Process: Fills out online proposal form
Tool: Online proposal form
Output: Submitted proposal

## Slide 12: Portfolio Formation – Step 2 Investigation
Actor: IT Director
Process: Cost Estimation (People / Dollars)
Tool: Evaluation Scorecard
Output: Cost information on Scorecard

## Slide 13: Portfolio Formation – Step 3 Scoring
Actor: Governance
Process: Objective Project Scoring (Impact & Risk)
Tool: Evaluation Scorecard
Output: Project Class & Impact, Project Swim Lane & Risk

## Slide 15: Project Classification (Prioritization)
Projects are scheduled
  Class X - Regulatory
  Class 0 - Underway
  Class 1 – High Impact / Low Cost = Quick Win
  Class 2 – High Impact / High Cost = Large Strategic
  Class 3 – Low Impact / Low Cost = Nice to Have
  Class 4 – Low Impact / High Cost = Declined

## Slide 16
Swim Lane (Required Level of Management)

## Slide 17: Portfolio Formation - Step 4 HL Scheduling
Actor: IT / PMO
Process: Resource Estimation & Capacity Planning
Tool: PPM
Output: Leveled Portfolio

## Slide 18: Portfolio Formation – Step 5 Approval
Actor: Governance / IT Leadership
Process: Portfolio Review and Approval
Tool: PPM
Output: Approved Portfolio

## Slide 19: Portfolio Tracking
SCOPE
TIME
COST
GANTT
Progress Reports
KPIs

## Slide 20: Portfolio Reporting
Dashboards
Review Meetings
Reports
Report Outs

## Slide 21: PM PROCESS
Swim Lanes
Stages
Stage Gates

## Slide 22
Swim Lane (Required Level of Management)

## Slide 23: Stages: Technology Services Service Life Cycle

## Slide 24: INFORMATION SYSTEM: PPM

## Slide 25: INFORMATION SYSTEM: PPM
Consider the Following…
  Web thin client – nothing installed (why in this day and age?)
  Aggregate Reporting & Dashboards
  Custom reports & custom data
  MS Project-like schedule interface (via Web client)
  Ability to import / export Project files
  Capacity Planning (a must)
  Outlook integration / team member home
  Mobile device integration
BIASED

## Slide 26: Support Strategy

## Slide 27: Support Strategy – Doing the Right Thing
Project Support Center
PMO Project Consultants
Community of Practice

## Slide 28: Support Strategy – Doing it RIGHT
Project Audits
Project Intervention (can be SUBTLE or DIRECT)

## Slide 29
Project Portfolio
PM Process
Information System (PPM / PM Info Sys)
Support Strategy

## Slide 30: QUESTIONS?