## Slide 1: Vendor Statements of Work: Your Role as an IT Professional
Theresa Rowe | March 2011

## Slide 2: The world of multi-sourcing
One way to get the work done is out-source with a Statement of Work (SOW).
Vendors will provide service, either short- or long-term, for your college or university, based on statement of work agreements.

## Slide 3: Your role as the “IT Pro”
What is the role of the college or university employee in managing the statement of work and making sure that the vendor delivers as promised?
Outsourced work is really a mix of in-source and outsource resources.

## Slide 4: Statement of work Defined
Formal document.
Describes work activities, deliverables and timeline.
Describes vendor action steps and university responsibilities.
Detailed requirements and pricing are usually included.

## Slide 5: The Basics
What will the vendor do?
How will the vendor do it?
How much will it cost?

## Slide 6: Areas typically addressed by a SOW:
Purpose.
Scope of work.
Detailed description of work.
Project timeline.
Deliverables.
Standards.
Special requirements.
Acceptance criteria.
Payment schedule.

## Slide 7: Purpose
Project motivations.
Why are we doing this project?
Generally court decisions support vendor responsibility limited to items expressly identified in the SOW.

## Slide 8: Scope of Work
Describes the exact nature of the work to be done.
What does “project start” look like?
What does “project done” look like?

## Slide 9: Work description
Describes how the work will be performed.
Location.
Hardware.
Software.
People.
Security.

## Slide 10: Project timeline
Period of performance.
Consider start, deadline, allowable time, billable hours and all aspects of scheduling.

## Slide 11: Deliverables
Description of specific deliverables and outputs.
Description of what is due and when.
Consideration of interim milestone deliverables.

## Slide 12: Standards
Description of internal and external standards.
Consider rules for legal and regulatory requirements: FERPA, ADA, Personally identifiable information, Payment Card Industry, etc.

## Slide 13: Special Requirements
Consider specialized workforce requirements, such as degrees or certifications for personnel.
Travel and expense requirements.
Insurance requirements, even after end of agreement.
Ownership of deliverables.
Third-parties and sub-contractors.
Non-disclosure agreements.

## Slide 14: Acceptance Criteria
Specifies how the buyer or receiver will determine if the products or services are acceptable.
What objective criteria will be used to state the work is acceptable?

## Slide 15: Payment Schedule and terms
Payments breakdown.
Consider linkage to acceptance criteria and project milestones.

## Slide 16: Types of agreements
Consider negotiating master business relationship agreement first.
In a hierarchy: General Contract Agreement, Professional Service Agreements, Statement of Work.
Campus standards for warranties, indemnities, and limitation of liability.

## Slide 17: Types of payments
Fixed fee
  Standard master single
  Standard master with multiple projects
Time and Material
Services

## Slide 18: Types of SOWs
Staff augmentation
Installation – hardware or software
System implementation
Design
Development
Outsourcing
Audit and review
Training

## Slide 19: What goes wrong?
Lack of –
  Detail – “Vendor will fix all problems”.
  Schedule with milestone dates.
  Performance standards.
  Data quality standards.
  Change control and scope creep control.
  Power to cancel.
  Payment tied to performance.
  Definition of required university responsibilities.
  Control of methods.

## Slide 20: Cancel and terminate
SOWs needs immediate termination or cancelation provisions.
Understand how the SOW relates to the Professional Services Agreement.
Cancelling the SOW does not cancel the PSA.

## Slide 21: Your role
Reviewing terms and conditions.
Negotiating the agreement.
Defining measurables.
Fulfillment of your end of the bargain.
Holding the vendor accountable.

## Slide 22: Resist sales pressure
Special deals if signed by vendor selected date.
Get the details.
Vendor SOWs are general outlines used for marketing or initial review.

## Slide 23: Match sow to psa
Resist signing the contract or PSA until a strong SOW is developed.
Negotiated PSA should include limitation of liability, disclaimers of warranties, indemnification and copyright language.
Don’t renegotiate or redo the legal language in the SOW.
Add language to the SOW that in the event of any conflicting language, the PSA terms are favored.

## Slide 24: Check sow language
Start with general overview.
Include firm schedule with milestone dates.
Use precise language.

## Slide 25: Let’s review samples

## Slide 26: THANK YOU Theresa Rowe rowe@oakland.edu