## Slide 1: Server Virtualization and Consolidation
Presented by
Mike Bradley, Systems Administrator
Kurt Giessel, Server Administrator
Introduction by
Tim Wrye, Director Instructional Computing

## Slide 2: Introduction
Virtualization presents an opportunity to reduce the costs of supporting and maintaining your data center by consolidating physical resources. We will road map our consolidation plan from researching virtualization technologies, selecting new hardware, to implementation and deployment of virtual hosts and guests.

## Slide 3: The Situation
Two distinct and separate data centers, Instructional and Administrative.
Support multiple services.
  eDirectory and Active Directory Services
  DNS
  Proxy
  File Shares
  Web Services
  Power and cooling and administrative overhead

## Slide 4: The Situation
Responsibility to effectively and efficiently use tax payer resources.
Rising costs of hardware, power and support.
Increasing demand for new and innovative technology.
Do "more with less."

## Slide 5: The Project: A Phased Approach
Planning and Research
Pre-deployment
Deployment
Summary and review
“The Future for Highline Community College”

## Slide 6: Planning and Research
February 2008
The Odd Couple:
A.T. was looking for a cost efficient way to replace retiring servers, save energy costs and reduce RACK-CLUTTER in the data center.
I.C. had been using the free VM Server version and ESX in a limited capacity and was looking for an opportunity to do virtualization in the “right way.”

## Slide 7: Planning and Research
Thirty day network consolidation survey was conducted by a VAR (what a dream!).
Survey Says!

## Slide 8: Planning and Research
We wanted a blade system for efficiency and consolidation and scalability.
Our choices were limited by our power constraints, 110 vs. 220.
We elected to review SUN and Hewlett-Packard
Selected the HP c3000 because of our familiarity with the hardware and management software iLO and SIM.
Hardware

## Slide 9: Planning and Research
Parallels Virtuozzo
XEN
Microsoft Hyper-V
VMWare esx
SUN xVM
Virtual Iron
Stoneware (desktop virtualization)
Software

## Slide 10: Planning and Research
Hewlett-Packard
Dell-Equallogic
VMWare ESX 3.5 Enterprise Edition
Final Solution
C3000 Enclosure
Eight- BL 460 Blades
2xIntel Quad CPU
16GB RAM
Physical interconnects.
PS5500e SAN (2)

## Slide 11: Pre Deployment: Planning and Testing
June 2008

## Slide 12: Pre Deployment: Planning and Testing
Received hardware from HP, racked and stacked in the datacenter.
Installed and setup switches, connections, and Vlans.
Comment: Interconnects versus virtual network connect. Virtual connect is probably worth the additional money.
Getting your head wrapped around the whole virtual thing.

## Slide 13: Pre Deployment: Planning and Testing
Installed VMware ESX Enterprise Edition - three times, hardware issues, update issues, and one more for good measure.
Comment: What the HAL!
Verify hardware and firmware is current and certified by VMWare. HP provided the latest mezzanine card which was due to be certified by VM for another 2-3 months (Oct 2008).

## Slide 14: Pre Deployment: Planning and Testing
Began testing the P2V, another setback, V2V fine, Windows P2V inconsistent, Linux P2V non-existent.
We explored third-party vConverters, no support for Linux conversions.
Generated support call to VMWare, “Phone tag and waiting game.”
Comment: VMWare tech support is great, very knowledgeable, thorough, and committed to resolving all issues (6-7 hour support call). Introduced to Virtual Converter Beta!

## Slide 15: Pre Deployment: Planning and Testing
Completed Pre-deployment and “testing” last week of January 2009

## Slide 16: Deployment (More Testing?)
P2V and V2V conversions going well.
Fifty-four total virtual machines distributed across three resource pools;
Production (Critical)
Production (Normal)
and Test.
February – March 2009

## Slide 17: Deployment (More Testing?)
We planned to convert 65-70 servers out of our combined 80 total.
Currently 54 virtual servers are running, of that number 20 are new or test boxes, watch the server sprawl.
The “Bad SANta” issue, MPC setback, VMware support comes though in the clinch.
Investigate new SAN solution to meet multiple needs within the enterprise; two Dell-Equallogic PS5500e SAN units, is our answer.
February – March 2009

## Slide 18: Summary: Lessons Learned so far…
VMWare training. Definitely, start your deployment immediately, before your new knowledge goes stale. The intricacies’ of VMWare configuration and tools or not real intuitive, you get better with practice.
If you choose a blade solution and a “virtual-connect“ network option is available, go for it. It will save time, simplify your network connectivity and reduce cable clutter and confusion.
April 2009

## Slide 19: Summary: Lessons Learned so far…
Work closely with your in-house partners, to avoid the “virtual roadblock.” The virtualization concept can be difficult for some to digest. Initially, we recommend you approach virtual entity as you would a physical.
Work closely with your VMWare hardware partner. Double check hardware and application compatibility and support.
April 2009

## Slide 20: Summary: Lessons Learned so far…
Power and cooling calculator from Microsoft Hyper-V Virtualization tools.
http://www.hyper-green.com
April 2009
Conversion goal at 53% estimate current annual savings, based on regional power costs, to be $19,468.00. The savings after 82% “full” conversion goal is estimated at $33,800.00 annually.

## Slide 22: Thank You
mbradley@highline.edu
kgiessel@highline.edu
twrye@highline.edu